## Overview
BharatGen Speech Translation Intern Plan (8 weeks)
Project Setup
Intern name | <fill in>
Mentor name | <fill in>
Start date (Week 0 Day 1) | <YYYY-MM-DD>
End date (computed)
Repo URL | <fill in>
GPU environment | RunPod (RTX 4090 or A40, persistent volume)
HF token configured? | No
End state
Working STT → Translate → TTS demo using BharatGen Shrutam-2 + AI4Bharat IndicTrans2 + BharatGen Sooktam-2, with a handoff package that lets the next intern start at Week 6, not Week 0. Week 0 is a 5-day Python+ML bootstrap; Weeks 1–7 are the working project.
Status summary (auto)
Total items | 98
Done | 29
In Progress | 0
Blocked | 0
Not Started | 69
% Complete | 29.59%

## Tracker
Week | Week Start | Section | Item | Description | Rationale (why this is here) | Owner | Status | Evidence / Link | Notes
Week 0 |  | Setup | HF account + accept gating | Create HF account; accept terms on bharatgenai/Shrutam-2, bharatgenai/sooktam2, ai4bharat/indictrans2-indic-en-1B and en-indic-1B. Generate access token; set HF_TOKEN env var. Async, before Day 1. | All three target models are gated or trust_remote_code. Token must be live before Day 1 or first model load fails. | Intern | Done
Week 0 |  | Setup | RunPod pod + persistent volume | Create RunPod account. Spin up a Pod with persistent volume attached (recommend 80-100 GB to fit HF cache for all 3 models + datasets). GPU template: RTX 4090 (24 GB, cheaper) or A40 (48 GB, headroom for Week 6 multi-model). Note: pod ID, volume ID, GPU type chosen — documented in repo README. | Inference benchmarks are meaningful only against a fixed environment. Pod + GPU template should not change across weeks. Persistent volume so models survive pod restarts (otherwise re-downloading IndicTrans2-1B + Shrutam-2 + Sooktam-2 every cold start wastes 30+ min). | Mentor | Done |  | Account created, pod will be created when required since it consumes credits
Week 0 |  | Setup | HF cache on persistent volume | On the Pod: `export HF_HOME=/workspace/.cache/huggingface` (or whatever the mount path is). Add to ~/.bashrc. Verify by loading a tiny model and checking the file lands on the persistent volume. | Default HF cache lives in container ephemeral storage — wiped on pod restart. Pointing HF_HOME at the volume means model downloads are one-time. This single line saves ~5 hours over the internship. | Intern | Not Started
Week 0 |  | Setup | Repo created | Create `bharatgen-speech-intern-2026` with week0/ through week7/ folders. Branch protection so reviews are mandatory. | Weekly commits make progress visible asynchronously. Removes the 'I lost my notebook' failure mode. | Mentor | Done
Week 0 |  | Setup | Tooling installed | Python 3.10, conda or uv, VS Code with Python + Jupyter extensions, ffmpeg, jupyter lab. | ffmpeg is a hidden dependency for librosa/torchaudio/soundfile. Installing on Day 0 avoids a Day-1 audio-loading bug that looks unrelated. | Intern | Done
Week 0 |  | Setup | Pre-reading (<=3 hours) | AI4Bharat blog post on IndicTTS/IndicASR. Skim Shrutam-2 + Sooktam-2 model cards. No notes required. | Builds vocabulary exposure so Day 3 concepts have anchor points. Retention is not the goal here. | Intern | Done |  | Mark Done at end of Week 0 — vocabulary surfaces correctly in reflection.md (attention, transformers)
Week 0 |  | Concept | Day 1: numpy - arrays, shape, dtype, broadcasting | How arrays differ from Python lists. What .shape and .dtype mean. Broadcasting rules: when do (3,1) and (1,4) combine to (3,4). | PyTorch tensors are numpy arrays + GPU + autograd. Master numpy first; PyTorch then feels 30% new, not 100% new. | Intern | Done
Week 0 |  | Concept | Day 1: Jupyter cells, kernels, magics | Cell execution order, kernel state, %time, %matplotlib inline. Why notebooks for exploration, scripts for production. | ML work lives in notebooks. Notebook mental model is different from script mental model — hidden kernel state causes 'works for me' bugs. | Intern | Done
Week 0 |  | Hands-on | Day 1: numpy exercises | Create arrays, slice, broadcast, dot product, reshape. 10 small exercises. Write down what .shape will be BEFORE running each cell. | Predicting shape before running is the discipline that prevents 80% of 'shape mismatch' bugs later. | Intern | Done
Week 0 |  | Hands-on | Day 1: venv + requirements.txt comfort | Create a fresh venv with uv or conda, install numpy/matplotlib/jupyter, freeze a requirements.txt. | Every later week installs more packages. Environment hygiene now prevents 'it worked yesterday' problems in Week 4. | Intern | Done
Week 0 |  | Concept | Day 2: matplotlib pyplot basics | fig, ax = plt.subplots(). plot(), scatter(), hist(), set_xlabel/set_ylabel/set_title. | Every week involves plotting something. Familiarity removes a recurring friction point. | Intern | Done
Week 0 |  | Hands-on | Day 2: three plot types | Plot a sine wave, a 1000-sample Gaussian histogram, a scatter of two correlated variables. Each plot labeled. | Three plot types cover ~80% of what he'll plot. Practiced once, available always. | Intern | Done
Week 0 |  | Hands-on | Day 2: read one library doc page end-to-end | librosa 'Core IO and DSP' page. Read every section. Try one example from each. | Reading docs is THE skill. Practicing it on a library he'll use next week is dual-purpose. | Intern | Done
Week 0 |  | Concept | Day 3: what is a 'model' in ML | A function with learned parameters. Input -> some math -> output. That's it for now. We won't train any — only run pre-trained ones. | Demystifies the word. Removes the 'how does it learn' anxiety which is not Week 0's problem. | Intern | Done
Week 0 |  | Concept | Day 3: what is a tensor (vs numpy array) | Same data structure (n-dim array of numbers), but: lives on GPU, tracks gradients (we won't use this in inference). For our purposes: numpy array on a graphics card. | 90% of 'PyTorch feels hard' is this conceptual confusion. Naming and dismissing it early saves a week. | Intern | Done
Week 0 |  | Concept | Day 3: what is a tokenizer | Converts text -> list of integers (tokens) so models can process it. Different models have different tokenizers. 'नमस्ते' might be 1 token or 5 tokens depending on the tokenizer. | Crucial framing for Weeks 2-5 where tokenizers appear repeatedly. One-paragraph mental model is enough. | Intern | Done
Week 0 |  | Concept | Day 3: training vs inference | Training: model learns from labeled data. Inference: model runs on new inputs. We do inference only for 7 weeks. Knowing what we're NOT doing scopes the work. | Bounds the scope explicitly. Pre-empts the 'should I train it' instinct that derails most first ML projects. | Intern | Done
Week 0 |  | Concept | Day 3: GPU vs CPU intuition | GPU = thousands of small parallel cores, great at matrix multiplications. CPU = few fast sequential cores. Neural network = millions of matmuls -> GPU is 10-100x faster. | Frames Day 5's GPU warm-up and every subsequent profiling discussion. Intuition first, mechanics later. | Intern | Done
Week 0 |  | Hands-on | Day 4: watch 3Blue1Brown NN videos ch. 1-3 | But what IS a Neural Network?', 'Gradient descent', 'What does backpropagation really do?'. ~60 min total. Watch, don't pause to implement. | Visual intuition for what's inside the model box. Watching is enough; implementing is for later if at all. | Intern | Done
Week 0 |  | Hands-on | Day 4: 1-page reflection in own words | Answer in his own words: 'What is a neural network? What does training mean? Why do we need data?' One page max. | Watching != understanding. Writing in own words tests retention and exposes gaps cheaply. THIS is the bootstrap diagnostic. | Intern | Done
Week 0 |  | Concept | Day 4: attention/transformers - 1-page primer | Single page only: transformers are a NN architecture good at sequences. Attention lets each token 'look at' other tokens. Read Jay Alammar 'Illustrated Transformer' intro (first 1/3 only). | One-page bird's-eye view so transformer vocabulary in Weeks 2-5 isn't entirely foreign. Don't go deep. | Intern | Done
Week 0 |  | Hands-on | Day 5: first PyTorch tensor | pip install torch. torch.tensor([1,2,3]). Move .to('cuda'). Print .shape, .dtype, .device. Matmul of two random 1000x1000 tensors on CPU vs GPU, time both. | Tactile first PyTorch experience. CPU-vs-GPU timing makes the Day-3 'why GPU' concept concrete. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week0/day5_pytorch_tensors.ipynb | torch.tensor created, moved to/from cuda; .shape/.dtype/.device printed
Week 0 |  | Hands-on | Day 5: run HF distilbert via pipeline() | from transformers import pipeline; pipe = pipeline('sentiment-analysis'); pipe('I love this'). Three lines. Print the output. | Easiest possible HF entry. No AutoModel/AutoTokenizer yet — just see that 'model goes brrr' works. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week0/day5_pytorch_tensors.ipynb | pipeline('sentiment-analysis') run on 2 sentences with prose explanation of the load/tokenize/inference flow
Week 0 |  | Hands-on | Day 5: first commit | Commit week0_bootstrap.ipynb to repo with all Day 1-5 exercises. First git push. | Repo hygiene begins. Friday review now has something to review. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX | Multiple commits to claude/setup-intern-project-FkRbX; week0_bootstrap.ipynb + day notebooks pushed
Week 0 |  | Deliverable | week0_bootstrap.ipynb + reflection.md | Single notebook covering Days 1-5 exercises. reflection.md = his 1-page NN explanation from Day 4. | Single artifact for the week. Reviewable in one sitting. Reflection.md is the diagnostic — if vague, slow Week 1 down. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week0 | Per-day notebooks (day1_numpy, day2_matplotlib_librosa, day3_ml_tokens_tensor, day5_pytorch_tensors) + reflection.md (NN, training, attention/transformers) committed. Intern split the single bootstrap notebook by day; deliverable spec accepted as 'Done'.
Week 0 |  | Anti-pattern | Don't: implement a NN from scratch | Skip 'build your own neural network in numpy' tutorials. Skip backprop derivations. | Optimization target for Week 0 is conceptual coverage, not building. Implementation is a Week-9+ activity (i.e., after this internship). | Intern | Done |  | No scratch-NN implementation in week0 notebooks
Week 0 |  | Anti-pattern | Don't: read PyTorch tutorials past 'Tensors' | Skip 'Autograd', 'Training a Classifier', 'Optimization'. Those are training-stack content; we don't train. | Inference-only scope. Reading training content now muddles the mental model. | Intern | Done |  | Day 5 stayed at tensor creation + device moves; no autograd
Week 0 |  | Anti-pattern | Don't: stress over 3Blue1Brown math | If gradient descent algebra is hard, that's fine. Watch for intuition; math doesn't gate Week 1. | Math fluency is not a Week-0 prerequisite. Sets expectations. | Intern | Done |  | Reflection captures intuition without algebra
Week 1 |  | Concept | Sampling rate: 16 kHz vs 44.1 kHz | What sampling rate means; why ASR models specify 16 kHz; what happens when you pass 44.1 kHz to a 16 kHz model. | Sample-rate mismatch is a top silent-failure mode. Spot it now, save 4 hours of debugging later. | Intern | Done
Week 1 |  | Concept | Mono vs stereo | Why speech models expect mono. How to convert stereo to mono in librosa/torchaudio. | Common preprocessing bug source. | Intern | Done
Week 1 |  | Concept | Waveform vs spectrogram, mel scale | Visual difference; what models actually consume; why mel rather than linear frequency. | Models consume spectrograms, humans see waveforms. Bridging this gap visually = fastest path to intuition. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/blob/claude/setup-intern-project-FkRbX/week1/week1_audio_basics.ipynb | Covered in week1_audio_basics.ipynb + mel-spec plots for 5 languages
Week 1 |  | Concept | Tensor basics in practice | tensor.to(device), .shape, .dtype, .cpu(), .numpy(). Why device-mismatched ops fail. | Builds on Week 0 Day 5 with more depth now that bootstrap context exists. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/blob/claude/setup-intern-project-FkRbX/week1/week1_tensors_matmul.ipynb | .shape/.dtype/.device/.to()/.numpy() walked through with examples
Week 1 |  | Hands-on | Record 5 clips in different languages | Phone recordings: Hindi, English, plus 3 of Marathi/Tamil/Kannada/Bengali. Save as WAV. | Real audio surfaces real preprocessing issues that synthetic test files don't. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week1/data/audio_clips | 5 .wav clips committed: English, Hindi, Kannada, Marathi, Telugu
Week 1 |  | Hands-on | Plot waveform and mel-spectrogram | Side-by-side plots in librosa. Zoom in on silence vs speech. Annotate which is which. | Visualization grounds the abstract. Annotation forces him to articulate what he sees. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week1/data/plots | Side-by-side waveform + mel-spectrogram PNGs for all 5 language clips
Week 1 |  | Hands-on | Resample 44.1 -> 16 kHz, listen to both | torchaudio.transforms.Resample. Listen and compare. Note what's lost. | Demonstrates that significant information loss is tolerable for intelligibility — frames why ASR standardized on 16 kHz. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/blob/claude/setup-intern-project-FkRbX/week1/resampling_16khz.ipynb | 48kHz->16kHz torchaudio resample with subjective listen-comparison notes
Week 1 |  | Hands-on | Time CPU vs GPU matmul (larger) | 10000x10000 matmul, CPU vs GPU. Compare to Week 0 Day 5's 1000x1000 numbers. | Quantifies how the gap grows with size. Concrete intuition for batching benefits later. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/blob/claude/setup-intern-project-FkRbX/week1/week1_tensors_matmul.ipynb | Benchmarks at 1000/2500/10000 matrix sizes, CPU vs GPU with synchronize()
Week 1 |  | Deliverable | week1_audio_basics.ipynb + audio_cheatsheet.md | Notebook with plots and annotations. 1-page cheatsheet: sampling rate, mono/stereo, resampling, mel-spectrogram. | Cheatsheet seeds the handoff package. Audience-of-two forces clarity. | Intern | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week1 | Both deliverable files present: week1_audio_basics.ipynb and audio_cheatsheet.md
Week 1 |  | Anti-pattern | Don't: read Stanford CS224S lectures | Skip the full course. Theory rabbit hole. | Three weeks can disappear into lectures with no code shipped. | Intern | Done |  | No detour into CS224S — stayed on librosa/torchaudio primitives
Week 1 |  | Anti-pattern | Don't: derive Fourier transforms | Pattern-match what librosa produces. Don't reinvent the FFT. | Not on the critical path to running BharatGen models. | Intern | Done |  | Used librosa/torch primitives directly; no FFT re-derivation
Week 2 |  | Concept | AutoModel / AutoTokenizer / AutoProcessor | The Auto* pattern in HF transformers. Three classes: model weights, text tokenizer, multimodal processor. | Once internalized, every new HF model card becomes 80% familiar. | Intern | Not Started
Week 2 |  | Concept | trust_remote_code=True - security | What this flag does: executes Python from the model repo. Implications for untrusted models. | Sooktam-2 in Week 4 requires this flag. Need intuition before flipping it. | Intern | Not Started
Week 2 |  | Concept | model.eval() and torch.no_grad() | Training mode vs inference mode. no_grad halves memory and speeds up inference because it stops tracking gradients. | Forgotten in ~50% of beginner inference code. Easy win. | Intern | Not Started
Week 2 |  | Concept | Tokens, logits, softmax - the output side | Token = integer the tokenizer produces. Logits = raw model output (one number per vocab token). Softmax converts logits to probabilities. Builds on Week 0 tokenizer concept. | Closes the loop on Week 0. Logits/softmax are the language of every generate() call. | Intern | Not Started
Week 2 |  | Concept | HF cache structure | Inspect ~/.cache/huggingface/hub/. Files: config.json, tokenizer files, weights. | Demystifies the 'magic' of from_pretrained. Helps diagnose disk-space issues later. | Intern | Not Started
Week 2 |  | Hands-on | Run distilbert manually (not pipeline) | Load distilbert with AutoModel/AutoTokenizer. Print raw logits, apply torch.softmax, see probabilities. Compare to pipeline()'s output. | Bridges Week 0's pipeline() experience with the manual API. He sees what pipeline() was doing. | Intern | Not Started
Week 2 |  | Hands-on | Run whisper-tiny on Week 1 audio | openai/whisper-tiny via transformers. Get transcriptions. | First speech model. Becomes Week 3 baseline for Shrutam-2 comparison. | Intern | Not Started
Week 2 |  | Hands-on | Read a config.json end-to-end | Identify and write in plain English what hidden_size, num_hidden_layers, vocab_size mean. | Builds intuition for what 'loading a model' actually involves. | Intern | Not Started
Week 2 |  | Deliverable | how_to_run_an_hf_model.md | Tutorial written FOR the next intern. Code, screenshots, pipeline() vs manual loading. | Writing-for-others is the strongest test of understanding. | Intern | Not Started
Week 2 |  | Anti-pattern | Don't: fine-tune anything | No LoRA, no PEFT, no full fine-tune. Inference-only. | Half-trained models with no documentation. Inference depth > training breadth here. | Intern | Not Started
Week 2 |  | Anti-pattern | Don't: pull in accelerate/bitsandbytes yet | Skip distributed and quantization libraries. | Premature optimization. Adds debugging surface without value. | Intern | Not Started
Week 3 |  | Concept | WER and CER | (insertions + deletions + substitutions) / reference length. Use jiwer library. | Only quantitative way to compare ASR systems. | Intern | Not Started
Week 3 |  | Concept | Code-mixing difficulty | Why Hindi-English code-mix breaks most ASR models: tokenizer coverage, training-data distribution. | India-specific. Where BharatGen most differentiates from Whisper. | Intern | Not Started
Week 3 |  | Concept | Beam search vs greedy decoding | Greedy = take highest-probability token each step. Beam = keep top-k partial sequences. One paragraph each. | Affects every .generate() call. Enough to know what knob to tweak. | Intern | Not Started
Week 3 |  | Hands-on | Run Shrutam-2 on real-world audio | 10 Hindi + 10 Tamil + 5 code-mixed clips. Real audio (YouTube, podcasts, his own recordings), NOT model card examples. | Real audio surfaces real failure modes. Model card examples are cherry-picked. | Intern | Not Started
Week 3 |  | Hands-on | Compute WER vs Whisper large-v3 | Same audio, same ground truth, both models. Tabulate WER per language. | Shrutam-2 in isolation is just numbers. Comparison gives meaning. | Intern | Not Started
Week 3 |  | Profiling | Latency, peak GPU memory, throughput | torch.cuda.max_memory_allocated(), wall-clock time, audio-seconds per inference-second. Note hardware and batch size. | Inference-stack thinking starts here. Discipline reused every subsequent week. | Intern | Not Started
Week 3 |  | Deliverable | week3_shrutam2_eval.md | WER table, profiling table, 5 transcription failures with his hypothesis on each. | 'Why did it fail?' forces reasoning about model behavior. | Intern | Not Started
Week 3 |  | Anti-pattern | Don't: try to 'improve' the model | No retraining, no domain adaptation. Evaluation only. | Improvement is meaningless before measurement is solid. | Intern | Not Started
Week 3 |  | Anti-pattern | Don't: report numbers without hardware context | Always note GPU, batch size, audio length, language. | A latency number without context is noise. | Intern | Not Started
Week 4 |  | Concept | Embeddings - what they are | A vector of numbers representing something (a token, a speaker, an image). Similar things -> similar vectors. Speaker embedding = vector representing one person's voice. | Foundational concept used everywhere from here. Defining explicitly prevents confusion in Week 4 onwards. | Intern | Not Started
Week 4 |  | Concept | Reference-guided voice conditioning | Sooktam-2 takes a reference WAV + reference transcript and produces a speaker embedding. The TTS is conditioned on it — output mimics the reference voice. | Distinguishes Sooktam-2 from description-conditioned TTS like Indic Parler. | Intern | Not Started
Week 4 |  | Concept | Vocoder vs acoustic model | Acoustic model: text -> mel-spectrogram. Vocoder: mel-spectrogram -> waveform. Two stages, two failure modes. | Helps reason about quality failures. Buzzy = vocoder. Wrong pronunciation = acoustic model. Different fixes. | Intern | Not Started
Week 4 |  | Concept | RTF (Real-Time Factor) | RTF = generation_time / audio_duration. RTF < 1 = faster than real-time. | Standard TTS metric. Lets him compare Sooktam-2 to Indic Parler on a common axis. | Intern | Not Started
Week 4 |  | Hands-on | Generate 3 languages x 3 reference voices | Hindi + Marathi + Tamil; three different reference speakers per language. | Reveals model behavior across language and speaker dimensions. | Intern | Not Started
Week 4 |  | Hands-on | Edge cases | Long target text (>500 chars). English loanwords in Hindi. Numbers and currency (2026, Rs.450). Code-mixed input. | These are where production deployments break. Document now. | Intern | Not Started
Week 4 |  | Hands-on | Compare with ai4bharat/indic-parler-tts | Same Hindi sentences, same listener. Reference-conditioned vs description-conditioned paradigms. | Forces articulating the trade-off. | Intern | Not Started
Week 4 |  | Profiling | Latency, RTF, GPU memory | Same profiling discipline as Week 3. | Builds the habit. | Intern | Not Started
Week 4 |  | Deliverable | week4_sooktam2_eval.md + audio samples | Markdown + committed audio. Indic Parler comparison. Tabulated profiling. Edge-case failure samples. | Claims about audio quality MUST be backed by listenable artifacts. | Intern | Not Started
Week 4 |  | Anti-pattern | Don't: claim quality without samples | Every quality assertion links to a WAV file. | Untestable claims become folk wisdom. | Intern | Not Started
Week 4 |  | Anti-pattern | Don't: forget reference clip quality is a ceiling | A noisy/unclear reference produces mediocre output regardless of model. | Garbage in, garbage out. Common beginner error. | Intern | Not Started
Week 5 |  | Concept | Sequence-to-sequence (seq2seq) | Input sequence -> output sequence. ASR is audio-seq -> text-seq. TTS is text-seq -> audio-seq. Translation is text-seq -> text-seq. Same family. | Naming the abstraction unifies three apparently different models. Reduces cognitive load. | Intern | Not Started
Week 5 |  | Concept | Encoder vs decoder | Encoder = reads the whole input and builds an internal representation. Decoder = generates output one token at a time, looking at encoder's representation. | Architecture intuition for why translation models look different from chatbot LLMs. | Intern | Not Started
Week 5 |  | Concept | Autoregressive generation | Generates token by token, each new token depends on previously generated tokens. Builds on Week 2 logits/softmax: at each step, model outputs logits, picks next token. | Connects to earlier softmax concept. Explains why latency scales with output length. | Intern | Not Started
Week 5 |  | Concept | Beam search - experienced | Now actually set num_beams=1, 4, 8. Observe output and latency changes. | Week 3 introduced concept; Week 5 experiences it. | Intern | Not Started
Week 5 |  | Hands-on | Run IndicTrans2 both directions | ai4bharat/indictrans2-indic-en-1B and en-indic-1B. 30 sentences across 4 languages. | Practical breadth. | Intern | Not Started
Week 5 |  | Hands-on | Edge cases | Technical/legal Hindi, casual WhatsApp text, numbers and dates, code-mixed input. | Tests robustness across registers. | Intern | Not Started
Week 5 |  | Hands-on | Round-trip translation | Hindi -> English -> Hindi for 10 sentences. Compare to originals for meaning drift. | Quick quality signal without expensive BLEU. | Intern | Not Started
Week 5 |  | Profiling | Latency, GPU memory, tokens/sec | Same profiling discipline. | Continuity. | Intern | Not Started
Week 5 |  | Deliverable | week5_indictrans2_eval.md + translate.py CLI | Eval doc + a small CLI: `python translate.py --src hi --tgt en --text "..."`. | First reusable tool. Imported into Week 6 pipeline. | Intern | Not Started
Week 5 |  | Anti-pattern | Don't: treat BLEU as the only metric | BLEU + round-trip + human spot-checks. | BLEU is brittle for morphologically rich Indic languages. | Intern | Not Started
Week 6 |  | Concept | Pipeline / model composition | How models compose. State between models (audio buffers, intermediate text, language metadata). | Composition has its own failure modes that individual models don't. | Intern | Not Started
Week 6 |  | Concept | GPU memory budgeting | Three models, finite GPU. Decision: keep all loaded, swap, or offload to CPU? Trade-offs. | The inference-stack lesson. The engineering judgment is what we want him to develop. | Intern | Not Started
Week 6 |  | Hands-on | Wire Shrutam-2 + IndicTrans2 + Sooktam-2 | Audio -> Shrutam-2 (Hindi audio -> Hindi text) -> IndicTrans2 (Hindi -> English) -> Sooktam-2 (English text -> English audio). | The actual goal of the internship. | Intern | Not Started
Week 6 |  | Hands-on | Gradio UI | File or mic input, source/target language dropdowns, audio player output. Run on localhost. | Makes the demo accessible to non-engineers. | Intern | Not Started
Week 6 |  | Hands-on | Decide GPU placement strategy | All three loaded? Lazy load? Evict between calls? Pick one, defend in writing, document. | Defending the choice is more valuable than picking the optimal one. | Intern | Not Started
Week 6 |  | Hands-on | Handle 3 failure modes only | Empty transcription. Very long input audio (>5 min). Translation timeout. | Bounded scope. Three well > fifteen poorly. | Intern | Not Started
Week 6 |  | Profiling | Pipeline-level latency | End-to-end wall clock for a 10s audio input. Per-stage breakdown. | Sets up Week 7's end-to-end profiling. | Intern | Not Started
Week 6 |  | Deliverable | Gradio demo + architecture.md | Hand-drawn architecture: data flow, model placements, memory budget, failure modes. | Drawing tests data-flow understanding. | Intern | Not Started
Week 6 |  | Anti-pattern | Don't: streaming or realtime | No WebSockets. Request-response only. | Streaming is its own multi-week project. | Intern | Not Started
Week 6 |  | Anti-pattern | Don't: containerize | No Docker. Plain Python + Gradio. | Containerization without deployment target is theater. | Intern | Not Started
Week 7 |  | Hands-on | End-to-end profiling: ms breakdown | For a 10s Hindi -> English audio task: total ms, ASR ms, translate ms, TTS ms, overhead ms. Single diagram. | Synthesizes every week's profiling. The diagram goes on the wall. | Intern | Not Started
Week 7 |  | Hands-on | Memory profiling | Peak GPU memory per model. Peak with all three loaded concurrently. Implication: GPU tier needed. | Concrete answer to a recurring product question. | Intern | Not Started
Week 7 |  | Hands-on | LIMITATIONS.md | Language coverage, code-mix failures, accent sensitivity, translation degradation, latency bottlenecks, GPU memory ceiling. | Honest scoping. Next intern starts knowing what doesn't work. | Intern | Not Started
Week 7 |  | Hands-on | Handoff README | Root README.md: 'How to run this in 30 minutes from scratch.' Step-by-step. | If new intern can't get to a working demo in 30 min, handoff failed. | Intern | Not Started
Week 7 |  | Hands-on | SETUP, EXPERIMENTS, NEXT_STEPS markdowns | SETUP: env/GPU/HF tokens. EXPERIMENTS: tried, worked, didn't. NEXT_STEPS: three concrete projects for next intern. | Decomposes the handoff into discoverable pieces. | Intern | Not Started
Week 7 |  | Hands-on | 30-min Loom walkthrough | Screen recording: demo the pipeline, walk through repo, point at limitations. | Watching is faster than reading for first-touch onboarding. | Intern | Not Started
Week 7 |  | Deliverable | Tagged repo v1.0-intern-handoff | git tag v1.0-intern-handoff. Final mentor review. | Discrete milestone. 'Done' is unambiguous. | Intern | Not Started
Week 7 |  | Anti-pattern | Don't: leave docs for the last day | Docs accumulate weekly from Week 1. | Week-7-only doc writing misses ~30% of what was done. | Intern | Not Started

## Glossary
Glossary
One-line definitions for every ML / audio / inference term used in the plan. Aimed at someone who's just finished Week 0. Use as a lookup, not as study material.
Category | Term | Plain-English definition | First appears
Audio | Sampling rate | How many audio measurements are taken per second. 16,000/sec (16 kHz) is the speech-model standard; CD audio is 44,100/sec. | Week 1
Audio | Waveform | The raw audio signal as a 1-D array of amplitude values over time. What you see in Audacity. | Week 1
Audio | Spectrogram | A 2-D image showing how energy at different frequencies changes over time. Models eat this, not the raw waveform. | Week 1
Audio | Mel-spectrogram | A spectrogram with frequencies rescaled to the mel scale (closer to how humans hear). Standard input for speech models. | Week 1
Audio | Mono / Stereo | Mono = 1 channel. Stereo = 2 channels. Speech models almost always want mono. | Week 1
PyTorch | Tensor | An n-dimensional array of numbers (like a numpy array) that can live on a GPU and support gradient tracking. For our purposes: numpy array on a graphics card. | Week 0
PyTorch | Device | Where a tensor lives: 'cpu' or 'cuda' (GPU). Operations between tensors on different devices fail. | Week 0
PyTorch | dtype | The numeric type of tensor elements: float32 (default), float16, bfloat16, int8, etc. Affects memory and precision. | Week 0
PyTorch | Broadcasting | Rules that let operations between tensors of different shapes work (e.g., adding (3,1) and (1,4) produces (3,4)). | Week 0
PyTorch | torch.no_grad() | A context manager that turns off gradient tracking. Use during inference: halves memory, speeds up. | Week 2
PyTorch | model.eval() | Switches a model from training mode to inference mode. Affects layers like dropout and batchnorm. | Week 2
ML | Model | A function with learned parameters. Input -> math -> output. For us, always pre-trained — we never train. | Week 0
ML | Parameters / Weights | The learned numbers inside a model. A '2.9B parameter model' has 2.9 billion of these. | Week 0
ML | Inference | Running a trained model on new inputs to get outputs. The only thing we do for 7 weeks. | Week 0
ML | Training | Adjusting model parameters using labeled data. We don't do this. | Week 0
ML | Forward pass | Running input through the model to produce output. The thing that happens during inference. | Week 0
NLP | Token | An integer that represents a chunk of text. Could be a word, a subword, a character, or even a byte. | Week 0
NLP | Tokenizer | Converts text -> list of tokens (integers). Each model ships with its own tokenizer. | Week 0
NLP | Vocabulary / vocab size | The set of all possible tokens the model knows. vocab_size is how many distinct tokens exist. | Week 2
NLP | Embedding | A vector of numbers representing something (a token, a speaker, an image). Similar things -> similar vectors. | Week 4
NLP | Logits | The raw numeric output of a model, one per vocab token. Higher = model thinks this token is more likely. | Week 2
NLP | Softmax | Converts logits into probabilities (each between 0 and 1, summing to 1). Normalization with exponentials. | Week 2
NLP | Hidden size | The width of the model's internal representations (e.g., 768 = each token is represented by a 768-number vector inside the model). | Week 2
NLP | Layer | One stage of the model's processing. A 12-layer transformer applies its core operation 12 times. | Week 2
NLP | Attention | The operation that lets each token in a sequence 'look at' (weight) every other token. The core of transformers. | Week 0 (primer)
NLP | Encoder | Part of a model that reads the whole input and builds a representation of it. | Week 5
NLP | Decoder | Part of a model that generates output token by token, often conditioned on an encoder's representation. | Week 5
NLP | Seq2seq | A model whose input is a sequence and output is a sequence. ASR, TTS, and translation are all seq2seq. | Week 5
NLP | Autoregressive | Generates output one token at a time, each new token depends on previously generated tokens. | Week 5
NLP | Greedy decoding | At each generation step, pick the single highest-probability token. Fast, sometimes suboptimal. | Week 3
NLP | Beam search | At each step, keep the top-k partial sequences. Slower but usually better output. | Week 3
NLP | KV cache | Stored intermediate states from previous generation steps. Speeds up autoregressive decoding; eats GPU memory linearly with output length. | Week 7
Speech | ASR / STT | Audio -> text. ASR (Automatic Speech Recognition) and STT (Speech-to-Text) mean the same thing. | Week 3
Speech | TTS | Text -> audio. Text-to-Speech. | Week 4
Speech | NMT | Neural Machine Translation. Text in one language -> text in another, done by a neural network. | Week 5
Speech | Acoustic model | In TTS, the part that turns text into a mel-spectrogram. | Week 4
Speech | Vocoder | In TTS, the part that turns a mel-spectrogram into an audible waveform. | Week 4
Speech | Reference-guided / voice cloning | TTS conditioned on a reference audio clip: the output mimics the reference speaker. | Week 4
Speech | Description-conditioned TTS | TTS conditioned on a text description ('a calm female voice with low pitch') rather than a reference clip. Indic Parler-TTS works this way. | Week 4
Speech | WER | Word Error Rate. (insertions + deletions + substitutions) / total reference words. Lower is better. | Week 3
Speech | CER | Character Error Rate. Same as WER but at character level. More forgiving for morphologically rich languages. | Week 3
Speech | RTF | Real-Time Factor. generation_time / audio_duration. RTF < 1 means faster than real-time. | Week 4
HF | Model card | The README on a Hugging Face model page. Documents usage, training data, intended use, limitations. | Week 0
HF | from_pretrained() | The HF method to download and load a model or tokenizer by ID. Caches in ~/.cache/huggingface/. | Week 2
HF | AutoModel / AutoTokenizer / AutoProcessor | Generic loaders that figure out the right model/tokenizer class from the model ID. | Week 2
HF | pipeline() | The highest-level HF interface. Three lines: load, call, get output. Hides AutoModel + AutoTokenizer + preprocessing. | Week 0
HF | trust_remote_code=True | Allows the model repo to execute its own Python code when loaded. Required by some models (Sooktam-2). Treat untrusted repos with caution. | Week 2
Engineering | Latency | Wall-clock time from input to output. Lower is better. | Week 3
Engineering | Throughput | How much work per unit time (audio-seconds processed per inference-second, or tokens/sec). | Week 3
Engineering | Peak GPU memory | The maximum GPU memory used during an operation. Measured with torch.cuda.max_memory_allocated(). | Week 3

## Deliverables
Week | Deliverable | Description | Why it matters | Status | Evidence / Link
Week 0 | week0_bootstrap.ipynb + reflection.md | Notebook covering numpy, matplotlib, first PyTorch tensor, first HF pipeline() call. reflection.md = 1-page 'what is a NN' in his own words. | Diagnostic for whether bootstrap landed. Vague reflection -> slow Week 1 down. | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week0
Week 1 | week1_audio_basics.ipynb + audio_cheatsheet.md | Audio plots + 1-page cheatsheet on sampling rate, mono/stereo, resampling, mel-spectrogram. | Cheatsheet seeds the handoff package. | Done | https://github.com/makarkul/bharatgen-speech-intern-2026/tree/claude/setup-intern-project-FkRbX/week1
Week 2 | how_to_run_an_hf_model.md | Tutorial: AutoModel/Tokenizer/Processor, cache, eval mode, no_grad. Code + screenshots. | Writing-for-others test of understanding. | Not Started
Week 3 | week3_shrutam2_eval.md | WER table (Shrutam-2 vs Whisper, per language), profiling table, 5 failure cases with hypotheses. | First quantitative comparison. Establishes the rigor bar. | Not Started
Week 4 | week4_sooktam2_eval.md + audio samples | Markdown + audio. Indic Parler comparison. Edge-case failures documented. | Quality claims backed by listenable artifacts. | Not Started
Week 5 | week5_indictrans2_eval.md + translate.py CLI | Translation eval + reusable CLI consumed by Week 6 pipeline. | First reusable artifact. | Not Started
Week 6 | Gradio demo + architecture.md | Click-through STT -> Translate -> TTS demo. Hand-drawn architecture diagram with memory budget and failure modes. | The actual goal. Drawing tests understanding. | Not Started
Week 7 | Tagged repo v1.0-intern-handoff | Complete handoff: README, SETUP, EXPERIMENTS, NEXT_STEPS, LIMITATIONS, 30-min Loom. | Next intern starts at Week 6, not Week 0. | Not Started

## Cadence
When | Activity | Duration | Format | Owner | Rationale
Monday morning | Intern posts the week's plan | 15 min | Async (Slack) | Intern | Forces intent-setting before the week starts. Monday corrections are cheap; mid-week corrections cost a day.
Wednesday | Blocker check (optional) | 10 min | Slack or call | Either | Mid-week safety net. Skip if not blocked. Prevents 'silently stuck Tue-Thu' pattern.
Friday EOD | Commit week's deliverable + 5-bullet progress note | Async | Git + Slack | Intern | Forced reflection. The 5 bullets become EXPERIMENTS.md timeline in Week 7.
Friday next day | Mentor reviews commits | 30 min | GitHub PR comments | Mentor | Async review. Schedules any Monday correction.
End of each week | Update Tracker status + evidence links | 5 min | This spreadsheet | Intern | Single source of truth for progress.
End of Week 0 | Mentor reads intern's reflection.md | 10 min | GitHub | Mentor | Bootstrap diagnostic. Vague reflection -> slow Week 1. Specific reflection -> proceed at planned pace.

## Success Criteria
Week-7 Success Questions
If the intern can answer these without hedging at the end of Week 7, the plan worked.
# | Question | What a good answer looks like | Intern's answer (Week 7)
1 | For a 10-second Hindi audio file end-to-end translated to English speech, where does the time actually go? Give it to me in milliseconds per stage. | Stage-by-stage breakdown: ASR ms, translation ms, TTS ms, overhead/copies ms, total ms. Hardware noted. Points at the dominant stage and explains why.
2 | Why can't we run all three models on a 16 GB GPU simultaneously without something giving? | Numbers: per-model peak GPU memory. Aggregate. Names the dominant consumer. Discusses fp16/bf16, offload, lazy load as mitigations.
3 | What's the difference between how Shrutam-2 and Whisper handle code-mixed Hindi-English, based on your measurements? | WER numbers on the same code-mixed test set. Qualitative observation: where each tokenizer breaks. Speculation about training-data distribution.
4 | Sooktam-2 is reference-guided. What does that mean for output quality, and what does it mean for inference latency compared to a description-conditioned model like Indic Parler-TTS? | Quality: bounded by reference clip quality. Latency: extra reference encoding pass, RTF numbers for both. Trade-off articulated.
5 | If I gave you a 30-minute audio file, what breaks and why? | Memory growth (KV cache or buffer). Context limits. Chunking strategy needed. Error compounding across chunks for translation stage.

## Anti-Patterns
Week | Don't do this | Why it's tempting | Why to avoid
Week 0 | Implementing a neural network from scratch in numpy | Feels like 'doing prerequisites properly'. | Week 0 is conceptual coverage, not building. Implementation can be a post-internship project.
Week 0 | Reading PyTorch tutorials past 'Tensors' | PyTorch.org's tutorials look authoritative. | Autograd / training tutorials are training-stack content. We don't train; reading them muddles the model.
Week 0 | Stressing over 3Blue1Brown's math | Math fluency feels prerequisite. | Watch for intuition, not algebra. Math doesn't gate Week 1.
Week 1 | Reading Stanford CS224S lectures front-to-back | Feels like 'doing prerequisites properly'. | Three weeks disappear into lectures with zero code shipped.
Week 1 | Trying to derive Fourier transforms before plotting one | First-principles instinct. | FFT math is not on the critical path to running BharatGen models.
Week 2 | Fine-tuning anything (LoRA, full, PEFT) | Most-talked-about thing in ML. | Half-trained checkpoints with no documentation. Inference depth > training breadth here.
Week 2 | Pulling in accelerate / bitsandbytes / vLLM | Sounds professional. | Adds debugging surface without solving a current problem.
Week 3 | Trying to 'improve' Shrutam-2 | WER is bad on some clips - instinct is to fix it. | Improvement is meaningless before measurement is solid.
Week 3 | Reporting numbers without hardware/batch context | Easy oversight in a hurry. | A number without context is noise.
Week 4 | Claiming TTS quality without samples | 'Sounds good' feels honest. | Untestable claims become folk wisdom.
Week 4 | Blaming the model when the reference clip is bad | Garbage in is harder to spot than garbage out. | Wastes weeks debugging the wrong thing.
Week 5 | Using BLEU as the only translation metric | It's the metric in every paper. | BLEU is brittle for morphologically rich Indic languages.
Week 6 | Streaming / realtime / WebSockets | Sounds impressive. | Streaming is its own multi-week project.
Week 6 | Docker / Kubernetes containerization | 'Production-ready' instinct. | Containerization without a deployment target is theater.
Week 7 | Leaving docs for the last day | Always tempting. | Doc-only-in-week-7 misses ~30% of what was done.

## Learning Resources
Learning Resources
Specific, named resources for each week's concepts. Curated, not exhaustive. Primary = required. Supplementary = if interested or stuck.
Phase | Topic | Priority | Resource | Type | Time | URL
Pre-start | RunPod basics | Primary | RunPod Pods Overview + Quickstart | Docs | 30 min | https://docs.runpod.io/pods/overview
Pre-start | BharatGen context | Primary | AI4Bharat blog (skim IndicASR/IndicTTS posts) | Blog | 1 hour | https://ai4bharat.iitm.ac.in/blog
Week 0 Day 1 | numpy | Primary | SciPy Lectures: NumPy | Course | 2 hours | https://lectures.scientific-python.org/intro/numpy/index.html
Week 0 Day 1 | numpy | Supplementary | NumPy Absolute Beginners guide | Docs | 45 min | https://numpy.org/doc/stable/user/absolute_beginners.html
Week 0 Day 1 | Jupyter | Primary | Real Python: Jupyter Notebook Introduction | Article | 30 min | https://realpython.com/jupyter-notebook-introduction/
Week 0 Day 1 | venv / uv | Primary | Astral uv: Getting Started | Docs | 20 min | https://docs.astral.sh/uv/getting-started/
Week 0 Day 2 | matplotlib | Primary | Matplotlib: Pyplot tutorial | Docs | 45 min | https://matplotlib.org/stable/tutorials/pyplot.html
Week 0 Day 2 | librosa (reading practice) | Primary | librosa: Tutorial | Docs | 1 hour | https://librosa.org/doc/latest/tutorial.html
Week 0 Day 3 | What is a 'model' | Primary | Stephen Wolfram: What Is ChatGPT Doing? (first third only — through 'Inside ChatGPT') | Essay | 1.5 hours | https://writings.stephenwolfram.com/2023/02/what-is-chatgpt-doing-and-why-does-it-work/
Week 0 Day 3 | Tokenizer concept | Primary | HF Tokenizers: Summary | Docs | 20 min | https://huggingface.co/docs/transformers/tokenizer_summary
Week 0 Day 3 | GPU vs CPU | Primary | NVIDIA blog: CPU vs GPU | Article | 15 min | https://blogs.nvidia.com/blog/whats-the-difference-between-a-cpu-and-a-gpu/
Week 0 Day 4 | Neural network intuition | Primary | 3Blue1Brown: Neural Networks (Ch 1-3) | Video | 60 min | https://www.youtube.com/playlist?list=PLZHQObOWTQDNU6R1_67000Dx_ZCJB-3pi
Week 0 Day 4 | Transformer primer | Primary | Jay Alammar: The Illustrated Transformer (first 1/3 only) | Article | 30 min | https://jalammar.github.io/illustrated-transformer/
Week 0 Day 5 | PyTorch tensors | Primary | PyTorch: Tensors tutorial (STOP after this — don't continue to Autograd) | Tutorial | 30 min | https://pytorch.org/tutorials/beginner/basics/tensorqs_tutorial.html
Week 0 Day 5 | HF pipeline() | Primary | HF LLM Course Ch 1.3: Transformers, what can they do? | Course | 45 min | https://huggingface.co/learn/llm-course/chapter1/3
Week 1 | Audio data fundamentals | Primary | HF Audio Course Unit 1: Working with audio data | Course | 2 hours | https://huggingface.co/learn/audio-course/chapter1/introduction
Week 1 | librosa examples | Supplementary | librosa: Audio examples gallery | Docs | browse | https://librosa.org/doc/latest/auto_examples/index.html
Week 2 | Using HF Transformers | Primary | HF LLM Course Ch 2: Using Transformers (AutoModel, AutoTokenizer, pipeline internals) | Course | 2-3 hours | https://huggingface.co/learn/llm-course/chapter2/1
Week 2 | Audio pipelines | Primary | HF Audio Course Unit 2: A gentle intro to audio applications | Course | 1 hour | https://huggingface.co/learn/audio-course/chapter2/introduction
Week 2 | Transformer architectures for audio | Supplementary | HF Audio Course Unit 3: Transformer architectures for audio | Course | 1 hour | https://huggingface.co/learn/audio-course/chapter3/introduction
Week 3 | ASR / WER | Primary | HF Audio Course Unit 5: Automatic Speech Recognition | Course | 2-3 hours | https://huggingface.co/learn/audio-course/chapter5/introduction
Week 3 | WER computation | Primary | jiwer library README | Docs | 15 min | https://github.com/jitsi/jiwer
Week 3 | Whisper context | Supplementary | OpenAI Whisper paper (skim) | Paper | 30 min | https://arxiv.org/abs/2212.04356
Week 4 | TTS fundamentals | Primary | HF Audio Course Unit 6: From text to speech | Course | 2 hours | https://huggingface.co/learn/audio-course/chapter6/introduction
Week 5 | Translation / seq2seq | Primary | HF LLM Course Ch 7.4: Translation | Course | 1.5 hours | https://huggingface.co/learn/llm-course/chapter7/4
Week 5 | Encoder-decoder deep dive | Primary | Jay Alammar: The Illustrated Transformer (full read this time) | Article | 1 hour | https://jalammar.github.io/illustrated-transformer/
Week 5 | IndicTrans2 context | Supplementary | IndicTrans2 paper (skim Sections 1-3) | Paper | 30 min | https://arxiv.org/abs/2305.16307
Week 6 | Speech-to-speech pipeline | Primary | HF Audio Course Unit 7: Putting it all together (speech-to-speech translation chapter) | Course | 2 hours | https://huggingface.co/learn/audio-course/chapter7/introduction
Week 6 | Gradio UI | Primary | Gradio Quickstart | Docs | 45 min | https://www.gradio.app/guides/quickstart
Week 6 | GPU memory management | Primary | PyTorch: CUDA semantics | Docs | 30 min | https://pytorch.org/docs/stable/notes/cuda.html
Week 7 | PyTorch profiling | Primary | PyTorch: Profiler recipe | Tutorial | 30 min | https://pytorch.org/tutorials/recipes/recipes/profiler_recipe.html
Week 7 | Technical writing structure | Primary | Diátaxis framework (4 doc types: tutorials, how-tos, reference, explanations) | Reading | 30 min | https://diataxis.fr/